## Sheet1
Q1
Week | Target/Progress | Difficulty | Challenges
2023-03-27 | Create project schedule/Trello | Easy
| Set up repository with starter files and basic readme | Easy
2023-04-03 | Create new webapp | Medium
| Create Devops pipeline and configure YAML | Medium
2023-04-10 | Ensure linux agent is working as it should | Medium
2023-04-17 | Ensure the pipeline runs sucessfully/ correct errors | Hard | original version of scikit learn not compatible with joblib file - have to update this
2023-04-24 | Ensure the pipeline runs sucessfully/ correct errors | Hard | new version of sci-kit learn not compatible with python 3.7 - need to reconfigure linux VM to run python 3.8
2023-05-01 | Video demo the project | Medium | installation of recording software needs approval from IT
| Complete the Readme | Easy
Goal: | Submit project by 08/01/2023
Q2
Submit project
Q3
Monitor project to ensure continued correct operation
Q4/ 1 Year
Monitor project to ensure continued correct operation
Formulas:
Week = [Week, row above]+7