## Sheet1
Week | Target/Progress | Challenges
2023-03-27 | Set up repository with starter files and basic readme
2023-04-03 | Create new webapp and Devops pipeline
2023-04-10 | Ensure linux agent is working as it should
2023-04-17 | Ensure the pipeline runs sucessfully/ correct errors | original version of scikit learn not compatible with joblib file - have to update this
2023-04-24 | Ensure the pipeline runs sucessfully/ correct errors | new version of sci-kit learn not compatible with python 3.7 - need to reconfigure linux VM to run python 3.8
2023-05-01 | Video demo the project/complete the readme | installation of recording software needs approval from IT
Goal: | Submit project by 08/01/2023
Formulas:
Week = [Week, row above]+7